## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Arya Dileep Kumar | 2025-01-12 | Dimension mismatch in cosine similarity calculations | Sprint 3 | Dev team | Data processing | Added padding to match dimensions | 2025-01-13 | Closed | Fixed
2 | Arya Dileep Kumar | 2025-01-23 | Slack alerts were sent twice for a single feedback | Sprint 4 | Dev team | Integration issue | Fixed duplicate function cell | 2025-01-23 | Closed | Fixed
3 | Arya Dileep Kumar | 2025-01-17 | Collaborative filtering was using interaction table instead of ativity table | Sprint 3 | Dev team | Logic error | Updated logic to use activity table for recommendations | 2025-01-19 | Closed | Fixed
4 | Arya Dileep Kumar | 2025-01-20 | Sentiment analysis not storing responses properly in database | Sprint 2 | Dev team | Database issue | Adjusted sql queries and tested storage | 2025-01-21 | Closed | Fixed
5 | Arya Dileep Kumar | 2025-01-20 | UI not displaying the recommendation pop up properly | Sprint 4 | Dev team | UI issue | Fixed front end integration and adjusted display time | 2025-01-20 | Closed | Fixed
6 | Arya Dileep Kumar | 2025-01-25 | Alerts missing guest Id in notifications | Sprint 4 | Dev team | Alert message format issue | Updated alert messages to include guest id | 2025-01-25 | Closed | Fixed
7 | Arya Dileep Kumar | 2025-01-27 | Slack alerts failed due to exposure of webhook url | Sprint 4 | Dev team | Exposure of confidential data to public | Created a new webhook url | 2025-01-27 | Closed | Fixed
8 | Arya Dileep Kumar | 2024-12-12 | Python version incompatibility | Sprint 1 | Dev team | wrong version of python installed | Downgraded python version from 3.13 to 3.11 for smooth library installation | 2024-12-13 | Closed | Fixed
9 | Arya Dileep Kumar | 2024-12-22 | wrong format of recommendation pop up | Sprint 3 | Dev team | Backend pop-up message logic issue | update the message fromat | 2024-12-24 | Closed | Fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others